## To Do List - POC
|  | To do list |  |  | SETUP >
2021-11-05
| Due Today: | 1
| Overdue: | 0
| Done | Description | Due Date | Priority | Assigned to
Tip: Enter a number greater than 1 in Done column when task is complete. | 1 | Initial Set up and git checkin | 2021-11-04 | High | Panda
| 1 | Timer funcationality in the UI | 2021-11-07 | High | Panda
| 1 | Integration of timer and quiz validation | 2021-11-06 | Medium | WIP
| 0 | Integration of timer and quiz validation | 2021-11-06 | Medium | Rajish
| 1 | Display Single Page Question and answer_UI on submit | 2021-11-07 | High | Rajish
| 1 | Modify submit funcatinality and save with time | 2021-11-13 | High | Panda
| 1 | Login and Logout functinality (Optional) | 2021-11-10 | Low | Panda
|  | Admin Page Display | 2021-11-07 | High | Panda
|  | Integration and regression testing | 2021-11-07 | High | Rajish
|  | POC Ready and Demo | 2021-11-08 | High | Panda & Rajish
Bootstap 4 upgrade
Enter a number 1 in Done column when task is complete
Select a drop down arrow, such as Assigned To or Priority, to Filter or Sort your To Do List items.
Tips do not print.

## Questions
Questions |  | Proposal | Solutions
1 | How question to display in UI ? | 19/10 : Panda Bootsrap carousel ? https://codepen.io/adsaikat/pen/ejNzwe Steeper? https://mdbootstrap.com/docs/b4/jquery/components/stepper/ Multi Step Form https://www.w3schools.com/howto/howto_js_form_steps.asp?
2 | Page level authenication
4 | Error handling
5 |  | typing carousal https://codepen.io/gschier/pen/jkivt https://schier.co/blog/simple-vanilla-javascript-typing-carousel
6 |  | SweetAlert pop for display
7 | Keeping Login Logout as funcatinality optional | Comment: 10/23: Panda
8 | Starting phrase | Hey User, I hope you are doing well. I think I might know you. You are from the "Partner Paradise" Team and working as a "developer". You are from "Odisha." My intelligence says, You love "travelling" and are good at "Photography". That's amazing. It's time to interact with your colleagues and see who wins If you think my memories are faded then please go to the registration section and update.
9 | variable timer for each questions | save in db and pull the time
10 | Prevent user to go back/ close once application starts
11 | Don't allow to user to enter directly to the controller/test page
12 | Ajax Error Handling | https://stackoverflow.com/questions/4707755/asp-net-mvc-ajax-error-handling
13 |  | Typed JS for Home Screen
https://mattboldt.com/demos/typed-js/
14 | Additonal | https://anijs.github.io/#tryit https://alvarotrigo.com/fullPage/
15 | Role Based Authentication in everyPage
16 | Admin Page
17 | User Information Display and Edit
18 | Session across the website
19

## Sheet1
ToDo
1. Pass ViewModel from mvc and convert into array JS
2. Display in TypedJS
3. Hide/Remove However to see the answer nav bar if Joke_API did not return
4. User Screen for Editing records/Hobby
5. Display the who Answered correctly when user submits (BackEnd)
6. Display the who Answered correctly when user submits (FrontEnd)
https://stackoverflow.com/questions/58121431/flying-balloon-animation
Flying baloon
7.Hint Section on the top: Disappear the two answer list
8
--------------------
https://github.com/mattboldt/typed.js/issues/396
https://stackoverflow.com/questions/31598309/typed-js-how-to-call-function-onclick-multiple-times

## Assignment Setup
Assignment Setup |  | < TO DO LIST
The data in the table below supplies the available choices for the Assigned To field. You can modify the entries or add new entries to customize this workbook to fit your needs.
Assigned To | Column1
Asish | Developer
Rajish | Technical Expert

## To Do List-RoadMap
|  | To do list |  |  | SETUP >
2021-11-05
| Due Today: | 1
| Overdue: | 0
| Done | Description | Due Date | Priority | Assigned to
Tip: Enter a number greater than 1 in Done column when task is complete. | 0 | architecture
| 0 | Angular
| 0 | Rich UI
| 0 | Optimise Code,Design Pattern and read and write time
User Hints and Points
.Core
Bootstarp 5
Enter a number 1 in Done column when task is complete
Select a drop down arrow, such as Assigned To or Priority, to Filter or Sort your To Do List items.
Tips do not print.